## S1 - Products Vs Testing Builds
Notes From Testing Team: ⇒ With this Sheet, We are trying to provide more visibility on the Status of the Different Product Builds those are provided for Testing. ⇒ 3 Sections: ⁕ Yet to Start - Builds Came for Testing but still Open/Paused. ⁕ In Progress - Currently under Testing. ⁕ Closed - Test Cycle Completed. ⇒ Please Use "Dev Comments" Sheet, If you need to provide Note / Concern / Priority / Deadline, for everybody's understanding if we have to negotiate with the Other Teams. ⇒ Build Notifications can be seen in the Sheet "Build Notification". | [7 empty] | #REF!
Builds - Yet to Start
| Product | FeatureSet Name | Owner | Test Cycle | Status | Build Provided Date | Comments
| LXRInsights | LXRInsights Aggregate Application 02July2018 | KP | Test Cycle 1 | Paused | 2018-07-02 | Completed with the Unique users Scenario. Need to Start Testing with Returned Users with Orders. Already spoke with Tejas and as it seems like the feature has to be Retested, I am Pausing further Testing on it.
| LXRInsights | LXRInsights - Creating CSV File to pass it to the UI | KP | Test Cycle 1 | Open | 2018-07-02 | TBD
| LXRPlugin | LXRPlugin Enhancements 13Jun18 | Chakri | Test Cycle 4 | Paused | 2018-08-07 | Google API Deprecated
| LXRReports | LXRReports - Channel Mix Analysis Implementation 7Aug18 | Chakri | Test Cycle 1 | Paused | 2018-08-07
| LXRInsights | LXRInsights - Complete Front End Functionality | KP | Test Cycle 1 | Open | 2018-08-27 | TBD
Builds - In Progress
| Product | FeatureSet Name | Owner | Test Cycle | Status | Build Provided Date | Comments
| LXRGuide | LXRGuide Enhancements 20Sep2018 | Anil | Test Cycle 2 | In Progress | 2018-10-03
| LXRGuide | LXRGuide Enhancements 16Oct2018 | Anil | Test Cycle 2 | In Progress | 2018-10-16
| LXRReports | LXRReports - AutoReports Enhancements - 18Oct2018 | Chakri | Test Cycle 1 | In Progress | 2018-10-18
Builds - Testing Closed
| Product | FeatureSet Name | Owner | Test Cycle | Status | Build Provided Date | Comments
| LXRPlugin | LXRPlugin Enhancements 13Jun18 | Chakri | Test Cycle 1 | Closed | 2018-06-13 | Test Cycle Closed
| LXRMarketplace | LXRMarketplace Micro-influencer Generates 20Jun18 | Chakri | Test Cycle 1 | Closed | 2018-06-20 | I am Stopping the Testing Micro Influencer Generator tool as it is taking too much time to process (more than 5 minutes sometimes it takes even 10 minutes also).
| LXRGuide | LXRGuide - API Upgradation 29June2018 | Anil | Test Cycle 1 | Closed | 2018-06-29 | Build Status: Green
| LXRReports | LXRReports WHATIF Feature 02July2018 | Chakri | Test Cycle 1 | Closed | 2018-07-02 | Test Cycle Closed
| LXRGuide | LXRGuide - Customer dashboard 02July2018 | Anil | Test Cycle 1 | Closed | 2018-07-02 | Test Cycle Closed
| LXRInsights | LXRInsights S3 Application 09May2018 | KP | Test Cycle 2 | Closed | 2018-07-04 | Did not Test 2 Modified Parameters as the functionality has not been finalized.
| LXRGuide | LXRGuide - Customer dashboard 02July2018 | Anil | Test Cycle 2 | Closed | 2018-07-05 | Build Status: Green
| LXRSEO | LXRSEO Enhancements 06July2018 | KP | Test Cycle 1 | Closed | 2018-07-06 | Covered only the New Enhancements but NOT the ones those were already moved to the Production. For the features which are already in Production will be tested by Chakrapani once he is available
| Mobile Apps - Android | Android - Backlinks Checker Enhancements 25Jun18 | KP | Test Cycle 2 | Closed | 2018-07-06 | Test Cycle Closed
| Mobile Apps - iOS | iOS - Backlinks Checker Enhancements 25Jun18 | KP | Test Cycle 2 | Closed | 2018-07-06 | Test Cycle Closed
| LXRGuide | LXRGuide - Payment Invoices 06July2018 | Anil | Test Cycle 1 | Closed | 2018-07-06 | Build Status: Green
| LXRMarketplace | LXRMarketplace Micro-influencer Generates 20Jun18 | Chakri | Test Cycle 2 | Closed | 2018-07-06 | Test Cycle Closed
| LXRMarketplace | LXRMarketplace - Backlinks Checker Enhancements 25Jun18 | KP | Test Cycle 2 | Closed | 2018-07-09 | WebServices Not Working
| LXRGuide | LXRGuide - Admin Panel Changes 10July2018 | Anil | Test Cycle 1 | Closed | 2018-07-10 | Test Cycle Closed
| LXRReports | LXRReports WHATIF Feature 02July2018 | Chakri | Test Cycle 2 | Closed | 2018-07-10 | Build Status: Green
| LXRSEO | LXRSEO Enhancements 06July2018 | KP | Test Cycle 2 | Closed | 2018-07-11 | Status: Closed Note: Covered only the New Enhancements but NOT the ones those were already moved to the Production. For the features which are already in Production will be tested by Chakrapani once he is available
| LXRGuide | LXRGuide - Enhancements 12July2018 | Anil | Test Cycle 1 | Closed | 2018-07-12 | Build Status: Green
| LXRReports | LXRReports - API Changes 12July18 | Chakri | Test Cycle 1 | Closed | 2018-07-12 | In order to test the Redis implementation, we need external tools, this might take some time. Hence, I'll be testing it once the testing of API up gradation is done. 2. I have completed the testing of Google and Bing Api changes and it is working as expected. The testing of auto reports is still in progress. Since, the google api is about to sunset tomorrow (07/25/2018) i've approved the status to green only for the API changes. The status for auto reports will be given once the testing is done for it.(Build Status: Green)
| Mobile Apps - iOS | iOS - Backlinks Checker Enhancements 25Jun18 | KP | Test Cycle 3 | Closed | 2018-07-13 | Build Status: Green
| Mobile Apps - Android | Android - Backlinks Checker Enhancements 25Jun18 | KP | Test Cycle 3 | Closed | 2018-07-13 | Build Status: Green
| LXRMarketplace | LXRMarketplace - Backlinks Checker Enhancements 25Jun18 | KP | Test Cycle 3 | Closed | 2018-07-16 | Build Status: Green
| LXRGuide | LXRGuide GSI Shopify - 18July2018 | KP | Test Cycle 1 | Closed | 2018-07-16 | Build Status: Green
| LXRGuide | LXRGuide Enhancements 16July2018 | Anil | Test Cycle 1 | Closed | 2018-07-16 | Build Status: Green
| LXRSEO | LXRSEO Enhancements 18July2018 | KP | Test Cycle 1 | Closed | 2018-07-18
| LXRMarketplace | LXRMarketplace Micro-influencer Generates 20Jun18 | Chakri | Test Cycle 3 | Closed | 2018-07-18 | when User uses Analyze MicroInfluencer tool, he could search for a keyword. Unfortunately in the case of where he wants to stop the previous keyword search, currently, there is no option to change to the particular keyword until all the search result have been processed. Can you please confirm the scenario.
| LXRPlugin | LXRPlugin Enhancements 13Jun18 | Chakri | Test Cycle 2 | Closed | 2018-07-19 | Test Cycle Closed
| LXRGuide | LXRGuide Enhancements 25July2018 | Anil | Test Cycle 1 | Closed | 2018-07-25 | Test Cycle Closed
| LXRPlugin | LXRPlugin Enhancements 13Jun18 | Chakri | Test Cycle 3 | Closed | 2018-07-25 | Test Cycle Closed
| LXRReports | LXRReports - AutoReports Enhancements 12July18 | Chakri | Test Cycle 2 | Closed | 2018-07-26
| LXRSEO | LXRSEO Enhancements 18July2018 | KP | Test Cycle 2 | Closed | 2018-07-30 | As it seems like most of the issues are getting ReOpened, I am stopping the Test Cycle 2 on LXRSEO Enhancements 18July2018.
| LXRReports | LXRReports - Before Redis - Performance Testing | KP | Test Cycle 1 | Closed | 2018-08-07 | TBD
| LXRSEO | LXRSEO Enhancements 18July2018 | KP | Test Cycle 3 | Closed | 2018-07-31 | Test Cycle Closed
| LXRSEO | LXRSEO Enhancements 18July2018 | KP | Test Cycle 4 | Closed | 2018-08-01 | Build Status: Green
| LXRMarketplace | LXRMarketplace Micro-influencer Generates 20Jun18 | Chakri | Test Cycle 4 | Closed | 2018-08-03 | Build Status: Green
| LXRGuide | LXRGuide Enhancements 25July2018 | Anil | Test Cycle 2 | Closed | 2018-08-07 | Test Cycle Closed
| LXRReports | LXRReports - facebook API Enhancements 09Aug2018 | Chakri | Test Cycle 1 | Closed | 2018-08-09 | Test Cycle Closed
| LXRReports | LXRReports - Facebook API Enhancements 09Aug2018 | Chakri | Test Cycle 2 | Closed | 2018-08-14
| LXRSEO | LXRSEO - Enhancements 14Aug2018 | KP | Test Cycle 1 | Closed | 2018-08-14 | Test Cycle Closed
| LXRGuide | LXRGuide Enhancements 25July2018 | Anil | Test Cycle 3 | Closed | 2018-08-17 | Test Cycle Closed
| LXRReports | LXRReports - AutoReports Enhancements 12July18 | Chakri | Test Cycle 3 | Closed | 2018-08-21 | Test Cycle Closed
| LXRSEO | LXRSEO - Enhancements 14Aug2018 | KP | Test Cycle 2 | Closed | 2018-08-24 | Test Cycle Closed. @Vemanna: Please discuss with the Team on Enhancement and let me know the conclusion whether it really goes into Enhancement or we need to take care of it. And also about the Pending Issues 1 Major: Schedulers are Running 2 Times. [We had this issue very long time back ago in which it was happening in only in Test Server and it is fine in Production. I need you to confirm whether it is the same issue or a different one. ------------------------------------------------------------------------------------------------------ From Vemanna: 1. Anil tried to fix that enhancement one but no luck. As of now, we are parking side that one based on the priority/severity. 2. I discussed with Anil regarding scheduler issue, in his local system is working fine. So we will see in production. 3. Regarding the Timestamp issue, we have checked in the local system, local testing server, and production server but the issue occurring only in the local testing server. Please ignore now, we will check once again in production after deploying this code.
| LXRGuide | LXRGuide Enhancements 27Aug2018 | Anil | Test Cycle 1 | Closed | 2018-08-27 | As per the commitments given to US Team, Changes in the Google Ads grader is of high Priority [3 Days]. Test Cycle closed.
| LXRGuide | LXRGuide Enhancements 28Aug2018 | Anil | Test Cycle 1 | Closed | 2018-08-28 | As per the commitments given to US Team, Changes in the Google Ads grader is of high Priority. So taken this build into consideration, after completing will move to "LXRGuide Enhancements 27Aug2018"
| LXRSEO | LXRSEO - Enhancements 28Aug2018 | KP | Test Cycle 1 | Closed | 2018-08-28 | Note: I just want to make a note that there can be a slight chance of a manual error while entering the Data and saving it into the Revenue Vs Spend Tab and saving it and I have discussed with Imaran and there willing to take the risk in which they have to check the data while creating the entry. Below is one of the examples for Manual Error.: ---> Entry Creation in the interface: NetElixir SEO Fee($): 2000 (Manual Entry) Hours: 10 (Manual Entry) Fee Per Hour($): 10 (Manual Entry) ---> In the Report, It will be shown as: NetElixir SEO Fee: $10/hours x 10 hours = $2000/month *** As per discussions, SEO Team should take care of this and make sure everything is proper every time.
| LXRGuide | LXRGuide Enhancements 28Aug2018 | Anil | Test Cycle 2 | Closed | 2018-08-28 | Build Status: Green
| LXRSEO | LXRSEO - Enhancements 28Aug2018 | KP | Test Cycle 2 | Closed | 2018-08-29 | Build Status: Green
| LXRGuide | LXRGuide GSI Woocommerce - 29Aug2018 | KP | Test Cycle 1 | Closed | 2018-08-29
| LXRGuide | LXRGuide Enhancements 31Aug2018 | Anil | Test Cycle 1 | Closed | 2018-08-31 | Build Status: Green
| LXRGuide | LXRGuide Enhancements 04Sep2018 | Anil | Test Cycle 1 | Closed | 2018-09-04 | Test Cycle Closed
| LXRGuide | LXRGuide Enhancements 06Sep2018 | Anil | Test Cycle 1 | Closed | 2018-09-06 | Test Cycle Closed
| LXRMarketplace | LXRMarketplace Teaser Deck and Other Enhancements - 06Sep2018 | KP | Test Cycle 1 | Closed | 2018-09-06 | Test Cycle Closed
| LXRGuide | LXRGuide Enhancements 06Sep2018 | Anil | Test Cycle 2 | Closed | 2018-09-11 | Build Status: Green
| LXRReports | LXRReports - AutoReports Enhancements 12July18 | chakri | Test Cycle 4 | Closed | 2018-09-14
| LXRMarketplace | LXRMarketplace Teaser Deck and Other Enhancements - 06Sep2018 | KP | Test Cycle 2 | Closed | 2018-09-14 | Test Cycle Closed
| LXRMarketplace | LXRMarketplace Teaser Deck and Other Enhancements - 06Sep2018 | KP | Test Cycle 3 | Closed | 2018-09-20 | Test Cycle Closed. Major Concern: On trying to Analyse the same Website (Ex: Walmart.com) multiple times at the same time sequentially, A continuous Inconsistent Behaviour has been observed Multiple times as provided below: Report Generated with all the required Slides. (Which is expected) Report generated skipping LXRSEO Slide. Analysis keeps on running and it has not stopped. Analysis completed and displayed the Download button. But on clicking the Download button the page got refreshed.
| LXRReports | LXRReports - AutoReports Enhancements 12July18 | chakri | Test Cycle 5 | Closed | 2018-09-21
| LXRMarketplace | LXRMarketplace Teaser Deck and Other Enhancements - 06Sep2018 | KP | Test Cycle 4 | Closed | 2018-09-24 | Test Cycle Closed -------------------------------------------- From Sagar: We discussed with Pavan / Tejas regarding new issues raised in this test cycle, we will fix the new issues in next build and we want move the current build into production. QA Team: Waiting for your approval.
| LXRSEO | LXRSEO - Enhancements 26Sep2018 | chakri | Test Cycle 1 | Closed | 2018-09-26 | Build Status: Green
| LXRGuide | LXRGuide Enhancements 20Sep2018 | Anil | Test Cycle 1 | Closed | 2018-09-20 | Test Cycle Closed
| LXRGuide | LXRGuide GSI Woocommerce - 29Aug2018 | KP | Test Cycle 2 | Stopped | 2018-09-24 | Due to GMC Issues, It was unable to complete Testing for Expected Behaviour. Dev Team have also been tried hard in order to get it done. Also tried with Live Account but no Luck. And Didnt get any response from GMC. So it moved to Production and will investigate if any issue comes up.
| LXRReports | LXRReports - AutoReports Enhancements 12July18 | Chakri | Test Cycle 1 | Closed | 2018-10-01
| Mobile Apps - Android | LXRMarketplace Services & DNS Checker Android App - 11Oct2018 | KP | Test Cycle 1 | Closed | 2018-10-11
| LXRReports | LXRReports Enhancements - 9 October 2018 | Chakri | Test Cycle 1 | Closed | 2018-10-09 | Test Cycle Closed
| LXRGuide | LXRGuide Enhancements 11Oct2018 | Anil | Test Cycle 1 | Closed | 2018-10-11 | Test Cycle Closed
| LXRMarketplace | LXRMarketplace Teaser Deck Enhancements - 18Oct2018 | KP | Test Cycle 1 | Closed | 2018-10-18 | Test Cycle Closed
| LXRMarketplace | LXRMarketplace Teaser Deck Enhancements - 18Oct2018 | KP | Test Cycle 2 | Closed | 2018-10-19 | Test Cycle Closed
| Mobile Apps - Android | LXRMarketplace Services & DNS Checker Android App - 11Oct2018 | KP | Test Cycle 2 | Closed | 2018-10-22 | Test Cycle Closed

## S2 - Build Notifications
Builds In Progress
Product | FeatureSet Name | # Test Cycle | Build Provided Date | Feature Description and Details
LXRGuide | LXRGuide Enhancements 20Sep2018 | Test Cycle 1 | 2018-09-20 | Build Notification: -Notification report in the Admin side Feature
LXRGuide | LXRGuide Enhancements 16Oct2018 | Test Cycle 2 | 2018-10-16 | Build Notification: - Fixed issues related to the Custom date range.
LXRReports | LXRReports - AutoReports Enhancements - 18Oct2018 | Test Cycle 1 | 2018-10-18 | Notification: 1. The issue with the YOY in weekly reports is fixed. 2. The issue with MTD values in SEM weekly report is fixed. 3. Changed column size of ADVERTISING_CHANNEL_SUBTYPE in campaign_structure, AW_ReportCampaign,campaign_segment tables.
LXRInsights | LXRInsights - Complete Front End Functionality | Test Cycle 1 | 2018-08-27 | TBD
Builds - Yet to Start
Product | FeatureSet Name | # Test Cycle | Build Provided Date | Feature Description and Details
LXRInsights | LXRInsights Aggregate Application 02July2018 | Test Cycle 1 | 2018-07-02 | Notifications: 1. 3 tables INTERACTIVE_CUSTOMER_ANALYSIS , INTERACTIVE_CUSTOMER_ANA_USER_DATA , AGG_USER_INFO 2. INTERACTIVE_CUSTOMER_ANALYSIS is product level data with country, device, hour, PPC type, user-type, day.0 3. AGG_USER_INFO is to store user-level data 4. INTERACTIVE_CUSTOMER_ANA_USER_DATA is user data with avg items and avg orders, visits.
LXRInsights | LXRInsights - Creating CSV File to pass it to the UI | Test Cycle 1 | 2018-07-02 | TBD
LXRPlugin | LXRPlugin Enhancements 13Jun18 | Test Cycle 1 | 2018-06-13 | 1. Created New button "Settings" in ribbon to set the number format like standard number and US number format. 2.Given option to choose Number Format in LXRPlugin Reports( Except Weekly/Monthly/Dashboard).
LXRReports | LXRReports - Channel Mix Analysis Implementation 7Aug18 | Test Cycle 1 | 2018-08-07 | 1. Channel Mix Analysis Implementation.
LXRInsights | LXRInsights - Complete Front End Functionality | Test Cycle 1 | 2018-08-27 | TBD
Formulas:
Build Provided Date = if([FeatureSet Name]="","",Vlookup([FeatureSet Name],Sheet3!A:E,4,0))

## S3 - Dev Comments - Note Conce
Dev Comments
⇒ Please use this Section, If you need to provide Note / Concern / Priority / Deadline, for everybody's understanding if we have to negotiate with the Other Teams.
Product | Note / Concern / Priority / Deadline issues

## Sheet3 (hidden)
Notation | Product | # Test Cycle | Build Provided Date | Feature Description and Details
LXRPlugin Enhancements 13Jun18 | LXRPlugin | Test Cycle 1 | 2018-06-13 | 1. Created New button "Settings" in ribbon to set the number format like standard number and US number format. 2.Given option to choose Number Format in LXRPlugin Reports( Except Weekly/Monthly/Dashboard).
LXRMarketplace Micro-influencer Generates 20Jun18 | LXRMarketplace | Test Cycle 1 | 2018-06-20 | A new Micro Influencer Generator tool is implemented
LXRGuide - API Upgradation 29June2018 | LXRGuide | Test Cycle 1 | 2018-06-29 | Build Notification: 1. API Upgradation from version v201710 to v201806
LXRInsights Aggregate Application 02July2018 | LXRInsights | Test Cycle 1 | 2018-07-02 | Notifications: 1. 3 tables INTERACTIVE_CUSTOMER_ANALYSIS , INTERACTIVE_CUSTOMER_ANA_USER_DATA , AGG_USER_INFO 2. INTERACTIVE_CUSTOMER_ANALYSIS is product level data with country, device, hour, PPC type, user-type, day.0 3. AGG_USER_INFO is to store user-level data 4. INTERACTIVE_CUSTOMER_ANA_USER_DATA is user data with avg items and avg orders, visits.
LXRReports WHATIF Feature 02July2018 | LXRReports | Test Cycle 1 | 2018-07-02 | Notifications: 1.Implemented What-If Analysis in paid channel screen. 2.UI changes in social dashboard
LXRGuide - Customer dashboard 02July2018 | LXRGuide | Test Cycle 1 | 2018-07-02 | Build Notification: 1. Fixed the issue posted in Bugzilla related to Customer dashboard.
LXRInsights - Creating CSV File to pass it to the UI | LXRInsights | Test Cycle 1 | 2018-07-02 | TBD
LXRInsights S3 Application 09May2018 | LXRInsights | Test Cycle 2 | 2018-07-04 | As per our discussion, S3 application the previous issues have been fixed. Two parameters are modified These two parameters fetched only for conversion is done Landing Track Id: It is the NE_TRACKING_INFO_ID fetched from NE_TRACKING_INFO based on userid and business Assoc Id of time in the cookie of the parameter ("_netelixir_se") Late Conversion 1: when previous session Id is not equal to current session Id 0: if above condition is not satisfied it is zero.
LXRGuide - Customer dashboard 02July2018 | LXRGuide | Test Cycle 2 | 2018-07-05 | Build Notification: 1. Fixed the issues related to OBF form.
LXRSEO Enhancements 06July2018 | LXRSEO | Test Cycle 1 | 2018-07-06 | Notifications: We should respect the "noindex" keyword in the webpage if any and ignore that in crawling and analyzing this page metrics. Example: <meta content = "noindex"> Fixed postion of sitegrader side navigation menu when scrolling. As discussed with KP, I listed out the issues fixed previously and moved into production before moved into the test environment. Please find below. Monthly analytics data duplicate insertion issue fixed. As per previous product call feedback, we have changed colors for Top Keywords, No Follow vs Do Follow and URLs with Low word count sections. Websites like diodedynamics.com, , we are unable to fetch the social data. Now issue got fixed. famouscookies.com Blog URL issue. This website does not have blog but it's redirecting to home page if you search for blog. So this issue got fixed. Modified blog content. Modified content in Sitegrader - Mobile section. Privacy policy content has been changed. Modified content in Sitegrader. Updated content and color coding in report and user interface given by Angel. Fixed issue on fetching screen shot when website loading time.
Android - Backlinks Checker Enhancements 25Jun18 | Mobile Apps - Android | Test Cycle 2 | 2018-07-06 | We have implemented 3 new features in SEO Backlink app. Which are 1. Login with Facebook, Gmail or manual sign up to capture user email. 2. Searched domain history - using this feature user can see his history(this is in local to device). 3. Tool usage analysis - we are storing tool usage details based on the number of entries. - I have fixed the test cycle -1 issues of SEO Backlink Android App. Please verify the bugs from shared sheet. and let me know if any issues. Later Build Updates: 1. 2.
iOS - Backlinks Checker Enhancements 25Jun18 | Mobile Apps - iOS | Test Cycle 2 | 2018-07-06 | We have implemented 3 new features in SEO Backlink app. Which are 1. login with Facebook or Gmail or manual sign up using this login we capturing user details and saving in our database. 2. A saved domain - using this feature user can see his history(this is in local we are doing). 3. Tool usage analysis - we are storing tool usage details in databased based on the number of time using our tool. - I have fixed the test cycle -1 issues of SEO Backlink IOS App. Please verify it. and let me know if any issues. Later Build Updates: 1. Link Expired
LXRGuide - Payment Invoices 06July2018 | LXRGuide | Test Cycle 1 | 2018-07-06 | Build Notification: 1. All Payment Invoice Changes.
LXRMarketplace Micro-influencer Generates 20Jun18 | LXRMarketplace | Test Cycle 2 | 2018-07-06 | Fixed the loading issue
LXRMarketplace - Backlinks Checker Enhancements 25Jun18 | LXRMarketplace | Test Cycle 2 | 2018-07-09 | Notification: Fixed the issues of LXRMarketplace - Inbounlink Checker Enhancements 25Jun18 : In iPad or iPhone, though the Authorization got failed, the user is able to download the file for the purchased set.(Services) User is not getting the report on mail after purchase. Payment Mail is coming. In Other devices it is working fine which from services(Common for all payment related tools). Please keep Bcc for all the mails(Common for all payments success). Login with Facebook using Phone Number: On trying to login using Facebook with this case, currently the apps are again showing the popup and ask the user to enter the Email which is again one more step.(Enhancement) Later Build Updates: 1. Webservices for mobile apps is working. Please test mobile app services
LXRGuide - Admin Panel Changes 10July2018 | LXRGuide | Test Cycle 1 | 2018-07-10 | Build Notification: 1. Admin Panel Changes.
LXRReports WHATIF Feature 02July2018 | LXRReports | Test Cycle 2 | 2018-07-10 | Fixed Issues in test-cycle-I.
LXRSEO Enhancements 06July2018 | LXRSEO | Test Cycle 2 | 2018-07-11 | Notifications: The above mentioned issues 1, 3 and 4 are fixed. I have changed the status of issues. Issue #5: As discussed, it is not valid. Issue #2: We are giving respect to no-follow and no-index in crawling code, other than that we didn't change anything. We will check this issue in production after deploying this code. As of now ignore this one. Comment From Vemanna: Issue #2: Need to Investigate: For LXRMarketplace.com, In our Local, it is showing 59 URLs but in Production, the count is 39 in which I am hoping it as a correct number. This scenario happening on the local server only, we had experienced earlier also. Hope it won't happen in production server. We will check this after deploying this code.
LXRGuide - Enhancements 12July2018 | LXRGuide | Test Cycle 1 | 2018-07-12 | Build Notification: Fixed issues related to the below mentioned features 1. Admin Panel Changes. Test Cycle 1 2. Task Notification Email Changes.
LXRReports - API Changes 12July18 | LXRReports | Test Cycle 1 | 2018-07-12 | 1. Google Adwords API Changes from 201708 to 201806 2. Bing API Changes v11 to v12 3. Redis implementation
iOS - Backlinks Checker Enhancements 25Jun18 | Mobile Apps - iOS | Test Cycle 3 | 2018-07-13 | I have fixed the test cycle -2 issues of SEO Backlink IOS App. Please verify it. and let me know if any issues. Later Build Updates: 1. Link Update 2. The iOS apps are pointed to the Production Services. 3.
Android - Backlinks Checker Enhancements 25Jun18 | Mobile Apps - Android | Test Cycle 3 | 2018-07-13 | I have fixed all the issues raised in test cycle two. Please test the app with updated apk file. Later Build Updates: 1. Updated apk
LXRMarketplace - Backlinks Checker Enhancements 25Jun18 | LXRMarketplace | Test Cycle 3 | 2018-07-16 | Notification: Fixed the issues raised in Test Cycle 2 of Backlinks Checker enhancements 25Jun18. Fixed the issues related to service for mobile apps.
LXRGuide GSI Shopify - 18July2018 | LXRGuide | Test Cycle 1 | 2018-07-16 | Support for Shopify in Shopping Initiator
LXRGuide Enhancements 16July2018 | LXRGuide | Test Cycle 1 | 2018-07-16 | Build Notification: 1. Payment Module Changes.
LXRSEO Enhancements 18July2018 | LXRSEO | Test Cycle 1 | 2018-07-18 | • After adding client by manager, client should get credentials through email. • Manager can able to "edit/view/delete" the client info. • Modified monthly report name.(Example Format: LXRSEO_Monthly_Report_TestCamp1_2018_Jul_17.xls ) • Once Monthly reports scheduler completed, we are notifying SEO team through email. • Normal Users: After Login it's instead of navigating to home page now we are navigating to history page and we have added one input and button same as SiteGrader page. From History user can analyse sitegrader.
LXRMarketplace Micro-influencer Generates 20Jun18 | LXRMarketplace | Test Cycle 3 | 2018-07-18 | Fixed the issues
LXRPlugin Enhancements 13Jun18 | LXRPlugin | Test Cycle 2 | 2018-07-19 | Issues fixed in Millions format.
LXRGuide Enhancements 25July2018 | LXRGuide | Test Cycle 1 | 2018-07-25 | Build Notification: 1. New UI for the Dashboard and Task manager.
LXRPlugin Enhancements 13Jun18 | LXRPlugin | Test Cycle 3 | 2018-07-25 | Issues fixed in Millions format.
LXRReports - AutoReports Enhancements 12July18 | LXRReports | Test Cycle 2 | 2018-07-26 | Build Notification: Fixed Issues in test-cycle-I and added new feachers 1. Redis implementation 2. Automate Reports 3. Functionality for selecting SearchEngine as Source Type w.r.t All Channel and Paid Channel Dashboard
LXRSEO Enhancements 18July2018 | LXRSEO | Test Cycle 2 | 2018-07-30 | Fixed Issues in test-cycle-I.
LXRSEO Enhancements 18July2018 | LXRSEO | Test Cycle 3 | 2018-07-31 | As we have discussed about the test cycle-2, Two issues are reopened. I have fixed it and given fresh build.
LXRSEO Enhancements 18July2018 | LXRSEO | Test Cycle 4 | 2018-08-01 | Fixed one major issue in previous test-cycle.
LXRMarketplace Micro-influencer Generates 20Jun18 | LXRMarketplace | Test Cycle 4 | 2018-08-03 | Fixed the test cycle 3 issues of Micro-influencer Generator. Issue no 9 is moved to enhancement.
LXRReports - Before Redis - Performance Testing | LXRReports | Test Cycle 1 | 2018-08-07 | Tested on Production Server
LXRGuide Enhancements 25July2018 | LXRGuide | Test Cycle 2 | 2018-08-07 | - Fixed the issues related to New UI for the Dashboard and Task manager. - Support for the JumpStart application related to New UI.
LXRPlugin Enhancements 13Jun18 | LXRPlugin | Test Cycle 4 | 2018-08-07 | Issues fixed in Millions format. Add new for testing Adwords API upgradation.
LXRReports - Channel Mix Analysis Implementation 7Aug18 | LXRReports | Test Cycle 1 | 2018-08-07 | 1. Channel Mix Analysis Implementation.
LXRReports - Facebook API Enhancements 09Aug2018 | LXRReports | Test Cycle 1 | 2018-08-09 | 1. Facebook API V.2.11 to V3.0. 2.Social PDF Report.
LXRReports - Facebook API Enhancements 09Aug2018 | LXRReports | Test Cycle 2 | 2018-08-14 | 1. Fixed the Test - 1 Cycle issues with Facebook API and Social PDF reports.
LXRSEO - Enhancements 14Aug2018 | LXRSEO | Test Cycle 1 | 2018-08-14 | Notifications: LXRSEO Email Reminders for guest users and signup but not payed users (dropped at payment page) through scheduler. We are sending emails two times per users, Once user registered or used (guest users) the tool, then after 2nd day and 7th day, we are sending an email to the user. Scheduler Time: 12:00 Note: For the first time we are sending email to all the guest users and not payed users. Scheduler Time: 13:00. Once it is fired successfully, we will remove this scheduler. Email Template: https://www.figma.com/file/YOiTKWYUduskbp4HO4gYGQjP/LXRSEO-Email?node-id=0%3A1 Email Template Content: https://docs.google.com/document/d/1Nl2QEKe4uIHvz73gGWT-JrZIeOPlXK6GxiGMQ9MsO6I/edit
LXRGuide Enhancements 25July2018 | LXRGuide | Test Cycle 3 | 2018-08-17 | Build Notification: 1. Fixed the issues related to New UI for the Dashboard and Task manager.
LXRReports - AutoReports Enhancements 12July18 | LXRReports | Test Cycle 3 | 2018-08-21 | Reason for Build: Fixed Bugs raised in Test Cycle 2 Except Redis implementation for Search Engine. Functionalities to be Tested: 1. Automate Reports 2. Functionality for selecting SearchEngine as Source Type w.r.t All Channel and Paid Channel Dashboard
LXRSEO - Enhancements 14Aug2018 | LXRSEO | Test Cycle 2 | 2018-08-24 | Notifications: Fixed Issues in test-cycle-I.
LXRInsights - Complete Front End Functionality | LXRInsights | Test Cycle 1 | 2018-08-27 | TBD
LXRGuide Enhancements 27Aug2018 | LXRGuide | Test Cycle 1 | 2018-08-27 | Build Notification: 1. New Weekly and Monthly reports functionality. Build Notification: There is no option to change the server time in 211 server so that we are providing a link to check the Weekly and Monthly reports for temporary purpose.
LXRGuide Enhancements 28Aug2018 | LXRGuide | Test Cycle 1 | 2018-08-28 | Build Notification: 1.Changes in the Google Ads grader.
LXRSEO - Enhancements 28Aug2018 | LXRSEO | Test Cycle 1 | 2018-08-28 | Please test the LXRSEO in local testing server(192.168.0.243:9091). Notifications: Implemented suggestion given by SEO Team. i.e We have added Revenue vs Spend tab in Periodic Report section of client dashboard. Based on the inputs given by the seo manager to a particular account, we are adding those metrics in Traffic Overview sheet of Monthly Reports. Manager can edit the record. And they should add the record from interface before scheduler creating the monthly report. Only seo manager can access this feature. Scheduler Timings: Analytics Data Fetching Scheduler: 3:00 Monthly Reports Creating Scheduler: 9:00 Table Name: seo_revenue_vs_spend Note: The date range which we are fetching in the database for Revenue vs Spend, from 3rd of last month to 1st of this month.
LXRGuide Enhancements 28Aug2018 | LXRGuide | Test Cycle 2 | 2018-08-28 | Build Notification: 1.Fixed the issues related to Changes in the Google Ads Grader.
LXRSEO - Enhancements 28Aug2018 | LXRSEO | Test Cycle 2 | 2018-08-29 | Notifications: Fixed Issues in test-cycle-I.
LXRGuide GSI Woocommerce - 29Aug2018 | LXRGuide | Test Cycle 1 | 2018-08-29 | Notifications: Support for WooCommerce in Shopping Initiator Adding default AdCopy in the new Shopping Campaign Adding all states in the US as target location in the new Shopping Campaign
LXRGuide Enhancements 31Aug2018 | LXRGuide | Test Cycle 1 | 2018-08-31 | Build Notification: Sanity check on Holiday Growth Booster.
LXRGuide Enhancements 04Sep2018 | LXRGuide | Test Cycle 1 | 2018-09-04 | Build Notification: 1. Bing Geo and Device reports
LXRGuide Enhancements 06Sep2018 | LXRGuide | Test Cycle 1 | 2018-09-06 | Build Notification: 1.New Feed Back form 2.New Product tour functionality
LXRMarketplace Teaser Deck and Other Enhancements - 06Sep2018 | LXRMarketplace | Test Cycle 1 | 2018-09-06 | Notification: Tools analysis report: Updated apache API from 3.8 to 3.17 caused modification(Services) for below tool analysis reports. Inbound Link Checker Competitor Analysis PageSpeed Insights Most Used Keywords URL Auditor Micro Influencer Generator. New Tool: Preliminary Search Marketing Analysis tool.(URL: http://192.168.0.243:7071/preliminary-search.html) Input: Client(*) , Competitor website URL(S) and client logo(*). Tool Feature: Pull metrics related to domain traffic and SEO performance and generate report in PowerPoint(.ppt) format. Data sources(API) to fetch metrics for domain Similar Web (All domains) Channel Performance. Paid Search Visits. Search Traffic by Engine Device Performance. LXRSEO(User domain): SEO Score Card. Site Errors Compare results in respective tool dashboards. Similar Web: https://pro.similarweb.com/#/home/modules Credentials: UserName: presales@netelixir.com Password: netelixir15 Date range for data is last 12 months(Refer tool dashboard date availability) LXRSEO: http://192.168.0.243:9091 Live data for domain.
LXRGuide Enhancements 06Sep2018 | LXRGuide | Test Cycle 2 | 2018-09-11 | Build Notification: - Fixed issues related to Feedback and product tour.
LXRReports - AutoReports Enhancements 12July18 | LXRReports | Test Cycle 4 | 2018-09-14 | Build Notification: 1. Fixed the issues w.r.t weekly reports.
LXRMarketplace Teaser Deck and Other Enhancements - 06Sep2018 | LXRMarketplace | Test Cycle 2 | 2018-09-14 | Fixed the test cycle 1 issues of build LXRMarketplace Teaser Deck and Other Enhancements. Modification in below report services (Modified constant fields). Keyword Performance Analyzer tool. Reports in Admin Pannel. LXRPlugin Adoption reports. ATE Reports.
LXRMarketplace Teaser Deck and Other Enhancements - 06Sep2018 | LXRMarketplace | Test Cycle 3 | 2018-09-20 | Fixed the issues of Test Cycle 2 of LXRMarketplace Teaser Deck and Other Enhancements (Sep 06, 2018). --------------------------------------------- As LXRSEO service end points had been changed, now LXRMarketplace using the new service endpoints and redeployed the test cycle 3 build with the changes.
LXRGuide Enhancements 20Sep2018 | LXRGuide | Test Cycle 1 | 2018-09-20 | Build Notification: -Notification report in the Admin side Feature
LXRReports - AutoReports Enhancements 12July18 | LXRReports | Test Cycle 5 | 2018-09-21 | Build Notification: 1. Fixed the issues w.r.t weekly reports.
LXRMarketplace Teaser Deck and Other Enhancements - 06Sep2018 | LXRMarketplace | Test Cycle 4 | 2018-09-24 | Fixed the issues of Test Cycle 3 of LXRMarketplace Teaser Deck and Other Enhancements (Sep 06, 2018).
LXRSEO - Enhancements 26Sep2018 | LXRSEO | Test Cycle 1 | 2018-09-26 | Notifications: Screen shots, keyword and Traffic parameters are not considering in the overall LXRSEO score. So we are not fetching screen shots, keyword data and traffic data for LXRM request. For LXRSEO, we are considering the above three parameters. Now we are fetching the data based on the source and domainId from mongodb. Fixed issues, while testing the Preliminary Search Tool in LXRMarketplace.
LXRGuide Enhancements 20Sep2018 | LXRGuide | Test Cycle 2 | 2018-10-03 | Build Notification: 1. Fixed the issues posted in bugzilla related to Admin Notifications report
LXRGuide GSI Woocommerce - 29Aug2018 | LXRGuide | Test Cycle 2 | 2018-09-24
LXRReports - AutoReports Enhancements 12July18 | LXRReports | Test Cycle 1 | 2018-10-01
LXRMarketplace Services & DNS Checker Android App - 11Oct2018 | Mobile Apps - Android | Test Cycle 1 | 2018-10-11 | LXRMarketplace: REST Service for DNS Checker App is developed and hosted in LXRMarketplace testing server, you can access service from below URL Service URL: http://192.168.0.243:7071/rest/mobile-dnslookup form-data: queryDomain: carrygreen.com ------------------------------------------------------ Android Notification: Now the DNS Checker Android App will use the LXRMarketplace service to get the DNS Lookup result. Kindly, test the app with all possible URL and verify the result. Please refer the LXRMarketplace DNS Lookup App for result validation.
LXRReports Enhancements - 9 October 2018 | LXRReports | Test Cycle 1 | 2018-10-09 | Build Notifications: 1) The issue with Keyword performance report is fixed. 2). The issue with MTD values of SEM Weekly report is fixed.
LXRGuide Enhancements 11Oct2018 | LXRGuide | Test Cycle 1 | 2018-10-11 | No Mail
LXRGuide Enhancements 16Oct2018 | LXRGuide | Test Cycle 2 | 2018-10-16 | Build Notification: - Fixed issues related to the Custom date range.
LXRMarketplace Teaser Deck Enhancements - 18Oct2018 | LXRMarketplace | Test Cycle 1 | 2018-10-18 | Notification: Preliminary Search Marketing Analysis Tool: New template format in presentation file suggested by Pre Sales team. All new suggestions are implemented and update .ppt format Number of site errors to be displayed is 4 in LXRSEO related metrics (Old is: 5). Below are the changes suggested by the sales team for the teaser deck: Slide 1 --> White background Slide 5 --> Change of text (Recent Awards/ Recent Press) Slide 6/7 --> Change to white background Slide 8 --> Change to White background Slide 1 and Slide 9 --> UPS Logo - should be removable
LXRMarketplace Teaser Deck Enhancements - 18Oct2018 | LXRMarketplace | Test Cycle 2 | 2018-10-19 | Notification: Fixed the issues of test Cycle 1 of LXRMarketplace Teaser Deck Enhancements (Oct 18, 2018).
LXRReports - AutoReports Enhancements - 18Oct2018 | LXRReports | Test Cycle 1 | 2018-10-18 | Notification: 1. The issue with the YOY in weekly reports is fixed. 2. The issue with MTD values in SEM weekly report is fixed. 3. Changed column size of ADVERTISING_CHANNEL_SUBTYPE in campaign_structure, AW_ReportCampaign,campaign_segment tables.
LXRMarketplace Services & DNS Checker Android App - 11Oct2018 | Mobile Apps - Android | Test Cycle 2 | 2018-10-22 | Please test the app for test cycle two. ---------------------------------------------------------------------------------------------------------------------------------- Notification: DNS Look Up Service: Fixed the issues of test cycle 1 of Rest service of DNS Look up tool from LXRMarketplace.